## Sheet1
This document now superseded.
See PK vital statistics document under Oselia.

## Measurements
TRAIL MEASUREMENTS |  |  |  |  | Measurement # | One |  | Two |  | Three
[6 empty] | 2017-10-14 |  | 2018-02-25 |  | 2018-02-25
MAIN TRAIL (6-FOOT WIDE)
| interval | cumulative
| 681.5 | 681.5 | Jct - red barracks trail |  |  | 688 | 688 | 675 | 675
| 97.5 | 779 | Culvert 1 |  |  | 114 | 802 | 81 | 756
| 482 | 1261 | Culvert 2 |  |  | 469 | 1271 | 495 | 1251
| 176.5 | 1437.5 | Bridge |  |  | 178 | 1449 | 175 | 1426
| 910 | 2347.5 | Jct - boys camp trail |  |  | 921 | 2370 | 899 | 2325
| 605 | 2952.5 | Big bend |  |  |  |  | 605 | 2930
| 255 | 3207.5 | Zig-zag |  |  |  |  | 255 | 3185
| 361.5 | 3569 | Jct - girls camp trail |  |  | 1238 | 3608 | 345 | 3530 |  | 1205
| 223 | 3792 | Sugar shack - uppermost canopy support |  |  | 220 | 3828 | 226 | 3756
|  | 3792 | FEET OF (6') MAIN TRAIL |  |  | 3828 |  | 3756 |  | 3787
4-FOOT WIDE TRAILS
|  | 620 | From sugar shack footbridge to back meadow (new barracks) |  |  | 623 |  | 617
|  | 969 | From old red barracks in woods to NW-most lake |  |  | 968 |  | 970
|  | 133 | From main trail to red barracks |  |  | 133
|  | 343.5 | From main trail to boys camp |  |  | 344 |  | 343
|  | 2065.5 | FEET OF 4-FOOT TRAILS
|  | 5857.5 | TOTAL FEET | OF TRAIL BUILT/UPGRADED
|  | 1.1094 | TOTAL MILES

## Remediation
Distances given as cumulative feet and feet from last landmark
Proceeding "clockwise" (i.e. from old volleyball courts to sugar shack)
Unconsolidated gravel |  |  |  | (Stones sliding underfoot, too little #411 put down)
From 218' to 520'
From culvert 1 to culvert 2
Culvert eroding
Culvert 1 |  | nearly 1 foot of erosion, upriver, north side of culvert
Culvert 2 |  | somewhat less than 1 foot of erosion, upriver face, north side of culvert
No rip-rap was placed alongside the upstream end of either culvert – I mentioned this last year but I don't know if it was communicated to Ben.
Water ponding on trail or flowing across trail
MAIN TRAIL
Landmark | Cumul. Feet | Net Feet
0 |  |  | MAIN TRAIL - START OF TRAIL AT OLD V'BALL COURTS
| 170 | 170
| 230 | 230
| 372 | 372
| 520 | 520
675 |  |  | JCT - RED BARRACKS TRAIL
| 675 | 0 |  | along right (E) side of trail to culvert 1; also along trail to red barracks
756 |  |  | CULVERT 1
| 926 | 170
| 1020 | 264
1251 |  |  | CULVERT 2
| 1280 | 29
1426 |  |  | BRIDGE
| 1685 | 259
| 1774 | 348
| 1796 | 370
| 1840 | 414
| 2040 | 614
| 2117 | 691
| 2190 | 764
2325 |  |  | JCT - BOYS CAMP TRAIL
| 2358 | 33
| 2402 | 77
| 2422 | 97
| 2520 | 195
| 2615 | 290
| 2705 | 380 |  | thru 2720
2930 |  |  | BIG BEND
| 3035 | 105 |  | thru 3045
3185 |  |  | ZIG ZAG
| 3185 | 0
| 3335 | 150
3530 |  |  | JCT - GIRLS CAMP TRAIL
| 3560 | 30 |  | abandoned road is draining across current trail
3756 |  |  | SUGAR SHACK
LAKES TRAIL
0 |  |  | START OF TRAIL
83
222 |  |  | CULVERT
| 320 | 98
| 398 | 176
| 418 | 196 |  | thru 435
| 455 | 233
| 496 | 274
| 509 | 287
| 525 | 303 |  | thru 548
| 598 | 376
| 640 | 418
| 725 | 503
| 862 | 640
970 |  |  | END OF TRAIL AT LAKE
BOYS CAMP TRAIL
0 |  |  | START OF TRAIL
| 165 | 165
| 235 | 235
| 280 | 280
343 |  |  | END OF TRAIL AT CAMP
ZIG ZAG TRAIL
0 |  |  | START OF TRAIL AT SUGAR SHACK
| 386 | 386
| 448 | 448 |  | thru 465
END OF TRAIL AT MEADOW (NEW BARRACKS)